## Sayfa1
RECYLE IT Task Dependencies |  |  | RECYLE IT Estimates
|  |  | Task |  | Optimistic (Hour) | Realistic (Hour) | Pessimistic (Hour)
Work Package | Task | Dependency | 1.1. Preliminary Work |  | 59 | 74 | 94
1.1. Preliminary Work | 1.1.1. UI Design |  | 1.1.1. UI Design |  | 15 | 25 | 30
1.1. Preliminary Work | 1.1.2. Achitectural Design | 1.1.1. | 1.1.2. Achitectural Design |  | 25 | 24 | 35
1.1. Preliminary Work | 1.1.3. Technical Documentation | 1.1.2. | 1.1.3. Technical Documentation |  | 7 | 9 | 9
1.1. Preliminary Work | 1.1.4. Team Indroduction | 1.1.3. | 1.1.4. Team Indroduction |  | 2 | 3 | 4
1.1. Preliminary Work | 1.1.5. Determining the Target Audience | 1.1.4. | 1.1.5. Determining the Target Audience |  | 10 | 13 | 16
1.2. Technical Analysis | 1.2.1. Current Computer Hardware Analysis | 1.1.4. | 1.2. Technical Analysis |  | 11 | 11 | 11
1.2. Technical Analysis | 1.2.2. Determining the Necessary Infrastructure Needs | 1.1.4. | 1.2.1. Current Computer Hardware Analysis |  | 2 | 3 | 4
1.2. Technical Analysis | 1.2.3. Adequacy Analysis of Resources | 1.1.4. | 1.2.2. Determining the Necessary Infrastructure Needs |  | 4 | 4 | 4
1.3.1. Authentikation Tasks | 1.3.1.1.Sign Up | 1.1.4. | 1.2.3. Adequacy Analysis of Resources |  | 5 | 4 | 3
1.3.1. Authentikation Tasks | 1.3.1.2. Sign In | 1.1.4. | 1.3. Dev |  | 286 | 292 | 316
1.3.1. Authentikation Tasks | 1.3.1.3. Forget Pass | 1.3.1.2. | 1.3.1.1.Sign Up |  | 11 | 12 | 15
1.3.2. Back-End | 1.3.2.1. User DataBase | 1.1.4. | 1.3.1.2. Sign In |  | 11 | 12 | 17
1.3.2. Back-End | 1.3.2.2. Company DataBase | 1.1.4. | 1.3.1.3. Forget Pass |  | 13 | 13 | 17
1.3.2. Back-End | 1.3.2.3. Offer DataBase | 1.1.4. | 1.3.2.1. User DataBase |  | 2 | 1 | 2
1.3.2. Back-End | 1.3.2.4. Comment and Evaluation DataBase | 1.1.4. | 1.3.2.2. Company DataBase |  | 2 | 2 | 2
1.3.2. Back-End | 1.3.2.5. Payment Management System | 1.1.4. | 1.3.2.3. Offer DataBase |  | 2 | 2 | 3
1.3.2. Back-End | 1.3.2.6. Chat Management System | 1.1.4. | 1.3.2.4. Comment and Evaluation DataBase |  | 3 | 3 | 2
1.3.3. Create Offer Module | 1.3.3.1. Create Offer Page | 1.3.2.3 | 1.3.2.5. Payment Management System |  | 10 | 11 | 12
1.3.4. Payment Module | 1.3.4.1. Front-End Developer 'Payment' | 1.2.4.2. 1.3.2.5. | 1.3.2.6. Chat Management System |  | 12 | 11 | 11
1.3.4. Payment Module | 1.3.4.2. Secure Payment | 1.1.4. | 1.3.3.1. Create Offer Page |  | 15 | 14 | 20
1.3.5. Main Page Module | 1.3.5.1. Frond-End Developer 'Main Page' | 1.1.4. | 1.3.4.1. Front-End Developer 'Payment' |  | 20 | 25 | 20
1.3.5. Main Page Module | 1.3.5.2. Artificial Intelligence Design | 1.3.5.1. | 1.3.4.2. Secure Payment |  | 20 | 25 | 20
1.3.6. Chat Module | 1.3.6.1. Frond-End Developer 'Message' | 1.3.6.2. 1.3.2.6. | 1.3.5.1. Frond-End Developer 'Main Page' |  | 23 | 25 | 30
1.3.6. Chat Module | 1.3.6.2. Encrypt Messages | 1.1.4. | 1.3.5.2. Artificial Intelligence Design |  | 30 | 25 | 27
1.3.7. Other Page Module | 1.3.7.1. Services Page | 1.3.7.1.1. 1.3.7.1.2. 1.3.7.1.3. | 1.3.6.1. Frond-End Developer 'Message' |  | 21 | 18 | 19
1.3.7. Other Page Module | 1.3.7.1.1. Food | 1.1.4. | 1.3.6.2. Encrypt Messages |  | 21 | 21 | 22
1.3.7. Other Page Module | 1.3.7.1.2. Beverages | 1.1.4. | 1.3.7.1. Services Page |  | 10 | 12 | 15
1.3.7. Other Page Module | 1.3.7.1.3. Agriculture | 1.1.4. | 1.3.7.1.1. Food |  | 7 | 6 | 9
1.3.7. Other Page Module | 1.3.7.2. Contact Us Page | 1.1.4. | 1.3.7.1.2. Beverages |  | 9 | 7 | 8
1.4. Other | 1.4.1. PM |  | 1.3.7.1.3. Agriculture |  | 3 | 5 | 6
1.4. Other | 1.4.2. TL |  | 1.3.7.2. Contact Us Page |  | 21 | 22 | 17
1.4. Other | 1.4.3. Non Dev | 1.1.4. | 1.4.6. DevOps |  | 20 | 20 | 20
1.4. Other | 1.4.4. QA | 1.4.4.1. | Total Work |  | 356 | 377 | 419
1.4. Other | 1.4.4.3. Regression Testing | 1.4.4.1 1.3.1.2. | 1.4.1. PM | 0.2 | 71.2 | 75.4 | 83.8
1.4. Other | 1.4.4.2. Functional Testing | 1.4.4.1 1.3.1.2. | 1.4.2. TL | 0.2 | 71.2 | 75.4 | 83.8
1.4. Other | 1.4.4.1. Planning | 1.1.4. | 1.4.3. Non Dev | 0.05 | 17.8 | 18.85 | 20.95
1.4. Other | 1.4.5. Bug Fix | 1.4.4.2. | 1.4.4.3. Regression Testing | 0.2 | 71.2 | 75.4 | 83.8
1.4. Other | 1.4.6. DevOps | 1.4.4.2. | 1.4.4.2. Functional Testing | 0.2 | 71.2 | 75.4 | 83.8
|  |  | 1.4.4.1. Planning | 0.1 | 35.6 | 37.7 | 41.9
|  |  | 1.4.5. Bug Fix | 0.25 | 89 | 94.25 | 104.75
|  |  | Grand Total |  | 427.2 | 452.4 | 502.8